## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes | WBS
1 | Yes | Manually Scheduled | Have a functioning Robot | 40 hrs | February 25, 2019 8:00 AM | March 1, 2019 5:00 PM |  | 1 |  | 1
2 | Yes | Auto Scheduled | Link Pi to Motor Controller | 12 hrs | February 25, 2019 8:00 AM | February 26, 2019 12:00 PM |  | 2 |  | 1.1
3 | Yes | Auto Scheduled | Pi to Communicate over Serial | 5 hrs | February 25, 2019 8:00 AM | February 25, 2019 2:00 PM |  | 3 |  | 1.1.1
4 | Yes | Auto Scheduled | Pi to Communicate with Motor Controller | 3 hrs | February 25, 2019 2:00 PM | February 25, 2019 5:00 PM | 3 | 3 |  | 1.1.2
5 | Yes | Auto Scheduled | Link Controller to Pi | 12 hrs | February 25, 2019 8:00 AM | February 26, 2019 12:00 PM |  | 3 |  | 1.2
6 | Yes | Auto Scheduled | Simple Controller APP | 1 hr | February 25, 2019 8:00 AM | February 25, 2019 9:00 AM |  | 4 |  | 1.2.1
7 | Yes | Manually Scheduled | Setup and test controller on PI | 4 hrs | February 26, 2019 8:00 AM | February 26, 2019 12:00 PM |  | 4 |  | 1.2.2
8 | Yes | Manually Scheduled | Control simple robot | 16 hrs | February 27, 2019 8:00 AM | February 28, 2019 5:00 PM |  | 2 |  | 1.3
9 | Yes | Auto Scheduled | Create program to control simple robot over the internet | 3 hrs | February 27, 2019 8:00 AM | February 27, 2019 11:00 AM | 2 | 3 |  | 1.3.1
10 | Yes | Manually Scheduled | Get Pi to Stream Video | 144 hrs | March 4, 2019 8:00 AM | March 27, 2019 5:00 PM | 1 | 1 |  | 2
11 | Yes | Auto Scheduled | Attach and Configure CAM to Pi | 1 hr | March 4, 2019 8:00 AM | March 4, 2019 9:00 AM |  | 2 |  | 2.1
12 | Yes | Auto Scheduled | Stream Video from Pi over Internet | 10 hrs | March 4, 2019 9:00 AM | March 5, 2019 11:00 AM | 11 | 2 |  | 2.2
13 | Yes | Auto Scheduled | Implement Stream into APP | 8 hrs | March 26, 2019 8:00 AM | March 26, 2019 5:00 PM | 11,14 | 2 |  | 2.3
14 | Yes | Manually Scheduled | Setup Final Web App to Control Movement | 128 hrs | March 4, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 | 1 |  | 3
15 | Yes | Auto Scheduled | Create APP | 24 hrs | March 4, 2019 8:00 AM | March 6, 2019 5:00 PM |  | 2 |  | 3.1
16 | Yes | Auto Scheduled | Link Pi to APP | 4 hrs | March 7, 2019 8:00 AM | March 7, 2019 12:00 PM | 15 | 2 |  | 3.2
17 | Yes | Manually Scheduled | Setting up Pan and Tilt | 32 hrs | March 8, 2019 8:00 AM | March 13, 2019 5:00 PM | 1 | 1 |  | 4
18 | Yes | Auto Scheduled | Create CAM mount | 12 hrs | March 8, 2019 8:00 AM | March 11, 2019 12:00 PM |  | 2 |  | 4.1
19 | Yes | Auto Scheduled | Attach CAM and Servos | 1 hr | March 11, 2019 1:00 PM | March 11, 2019 2:00 PM | 18 | 2 |  | 4.2
20 | Yes | Auto Scheduled | Program CAM to Move | 5 hrs | March 11, 2019 2:00 PM | March 12, 2019 10:00 AM | 19 | 2 |  | 4.3
21 | Yes | Manually Scheduled | Ultrasonic Sensor | 1 hr | March 13, 2019 8:00 AM | March 13, 2019 9:00 AM | 1 | 1 |  | 5
22 | Yes | Auto Scheduled | Program Pi to Use Ultrasonic Sensor | 1 hr | March 13, 2019 8:00 AM | March 13, 2019 9:00 AM |  | 2 |  | 5.1
23 | Yes | Auto Scheduled | Collision Detection | 1 hr | March 19, 2019 8:00 AM | March 19, 2019 9:00 AM | 27,21,1 | 1 |  | 6
24 | Yes | Auto Scheduled | Use Ultrasonic Sensor for Collision Detection | 1 hr | March 19, 2019 8:00 AM | March 19, 2019 9:00 AM |  | 2 |  | 6.1
25 | Yes | Manually Scheduled | Photoresistor linking to CAM | 2 hrs | March 27, 2019 8:00 AM | March 27, 2019 10:00 AM | 1,10 | 1 |  | 7
26 | Yes | Auto Scheduled | Photoresistor for nightvision switch | 2 hrs | March 27, 2019 8:00 AM | March 27, 2019 10:00 AM |  | 2 |  | 7.1
27 | Yes | Manually Scheduled | Creating Frame and Components | 88 hrs | March 4, 2019 8:00 AM | March 18, 2019 5:00 PM | 1 | 1 |  | 8
28 | Yes | Auto Scheduled | Design Frame in CAD | 16 hrs | March 4, 2019 8:00 AM | March 5, 2019 5:00 PM |  | 2 |  | 8.1
29 | Yes | Auto Scheduled | 3D Print Frame | 24 hrs | March 6, 2019 8:00 AM | March 8, 2019 5:00 PM | 28 | 2 |  | 8.2
30 | Yes | Auto Scheduled | Attach Motors to Frame | 1 hr | March 11, 2019 8:00 AM | March 11, 2019 9:00 AM | 29 | 2 |  | 8.3
31 | Yes | Manually Scheduled | Additional Modules | 40 hrs | March 27, 2019 8:00 AM | April 2, 2019 5:00 PM | 1,27,10,14,17,21,23,25 | 1 |  | 9
32 | Yes | Auto Scheduled | Temperature Censor | 8 hrs? | March 27, 2019 8:00 AM | March 27, 2019 5:00 PM |  | 2 |  | 9.1
33 | Yes | Auto Scheduled | Self Driving | 8 hrs? | March 27, 2019 8:00 AM | March 27, 2019 5:00 PM |  | 2 |  | 9.2
34 | Yes | Auto Scheduled | Object Recognition | 8 hrs? | March 27, 2019 8:00 AM | March 27, 2019 5:00 PM |  | 2 |  | 9.3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | WBS | Notes
1 | Raspberry Pi | R | Material | [5 empty] | $0.00 | 1
2 | Wheels | W | Material | [5 empty] | $0.00 | 1.1
3 | Motor Controller | M | Material | [5 empty] | $0.00 | 1.1.1
4 | Servos | S | Material | [5 empty] | $0.00 | 1.1.2
5 | DC Motors | D | Material | [5 empty] | $0.00 | 1.2
6 | Camera | C | Material | [5 empty] | $0.00 | 1.2.1
7 | Ultrasonic sensor | U | Material | [5 empty] | $0.00 | 1.2.2
8 | 3D printer | 3 | Material | [5 empty] | $0.00 | 1.3
9 | Photoresistor | P | Material | [5 empty] | $0.00 | 1.3.1
10 | Frame materials | F | Material | [5 empty] | $0.00 | 2
11 | Breadboard | B | Material | [5 empty] | $0.00 | 2.1
12 | Jumper wires | J | Material | [5 empty] | $0.00 | 2.2
13 | Prototype Frame | P | Material | [5 empty] | $0.00 | 2.3
3
3.1
3.2
4
4.1
4.2
4.3
5
5.1
6
6.1
7
7.1
8
8.1
8.2
8.3
9
9.1
9.2
9.3

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units | WBS
Have a functioning Robot | Raspberry Pi | 0 | 1 | 1 | 1
Have a functioning Robot | Wheels | 0 | 1 | 1 | 1.1
Have a functioning Robot | Motor Controller | 0 | 1 | 1 | 1.1.1
Have a functioning Robot | DC Motors | 0 | 1 | 1 | 1.1.2
Have a functioning Robot | Prototype Frame | 0 | 1 | 1 | 1.2
Link Pi to Motor Controller | Motor Controller | 0 | 1 | 1 | 1.2.1
Link Pi to Motor Controller | Raspberry Pi | 0 | 1 | 1 | 1.2.2
Pi to Communicate over Serial | Raspberry Pi | 0 | 1 | 1 | 1.3
Pi to Communicate with Motor Controller | Motor Controller | 0 | 1 | 1 | 1.3.1
Pi to Communicate with Motor Controller | Raspberry Pi | 0 | 1 | 1 | 2
Link Controller to Pi | Raspberry Pi | 0 | 1 | 1 | 2.1
Control simple robot | Raspberry Pi | 0 | 1 | 1 | 2.2
Control simple robot | Motor Controller | 0 | 1 | 1 | 2.3
Control simple robot | Prototype Frame | 0 | 1 | 1 | 3
Get Pi to Stream Video | Camera | 0 | 1 | 1 | 3.1
Get Pi to Stream Video | Raspberry Pi | 0 | 1 | 1 | 3.2
Attach and Configure CAM to Pi | Camera | 0 | 1 | 1 | 4
Attach and Configure CAM to Pi | Raspberry Pi | 0 | 1 | 1 | 4.1
Stream Video from Pi over Internet | Camera | 0 | 1 | 1 | 4.2
Stream Video from Pi over Internet | Raspberry Pi | 0 | 1 | 1 | 4.3
Implement Stream into APP | Camera | 0 | 1 | 1 | 5
Implement Stream into APP | Raspberry Pi | 0 | 1 | 1 | 5.1
Setup Final Web App to Control Movement | Motor Controller | 0 | 1 | 1 | 6
Setup Final Web App to Control Movement | Raspberry Pi | 0 | 1 | 1 | 6.1
Setup Final Web App to Control Movement | Wheels | 0 | 1 | 1 | 7
Setup Final Web App to Control Movement | DC Motors | 0 | 1 | 1 | 7.1
Create APP | Raspberry Pi | 0 | 1 | 1 | 8
Link Pi to APP | Raspberry Pi | 0 | 1 | 1 | 8.1
Link Pi to APP | DC Motors | 0 | 1 | 1 | 8.2
Link Pi to APP | Motor Controller | 0 | 1 | 1 | 8.3
Link Pi to APP | Wheels | 0 | 1 | 1 | 9
Setting up Pan and Tilt | Breadboard | 0 | 1 | 1 | 9.1
Setting up Pan and Tilt | Camera | 0 | 1 | 1 | 9.2
Setting up Pan and Tilt | Jumper wires | 0 | 1 | 1 | 9.3
Setting up Pan and Tilt | Raspberry Pi | 0 | 1 | 1
Setting up Pan and Tilt | Servos | 0 | 1 | 1
Setting up Pan and Tilt | 3D printer | 0 | 1 | 1
Create CAM mount | 3D printer | 0 | 1 | 1
Attach CAM and Servos | Servos | 0 | 1 | 1
Program CAM to Move | Breadboard | 0 | 1 | 1
Program CAM to Move | Camera | 0 | 1 | 1
Program CAM to Move | Jumper wires | 0 | 1 | 1
Program CAM to Move | Raspberry Pi | 0 | 1 | 1
Program CAM to Move | Servos | 0 | 1 | 1
Ultrasonic Sensor | Ultrasonic sensor | 0 | 1 | 1
Ultrasonic Sensor | Frame materials | 0 | 1 | 1
Ultrasonic Sensor | Raspberry Pi | 0 | 1 | 1
Program Pi to Use Ultrasonic Sensor | Frame materials | 0 | 1 | 1
Program Pi to Use Ultrasonic Sensor | Raspberry Pi | 0 | 1 | 1
Program Pi to Use Ultrasonic Sensor | Ultrasonic sensor | 0 | 1 | 1
Collision Detection | Ultrasonic sensor | 0 | 1 | 1
Collision Detection | Raspberry Pi | 0 | 1 | 1
Collision Detection | Frame materials | 0 | 1 | 1
Use Ultrasonic Sensor for Collision Detection | Frame materials | 0 | 1 | 1
Use Ultrasonic Sensor for Collision Detection | Raspberry Pi | 0 | 1 | 1
Use Ultrasonic Sensor for Collision Detection | Ultrasonic sensor | 0 | 1 | 1
Photoresistor linking to CAM | Raspberry Pi | 0 | 1 | 1
Photoresistor linking to CAM | Photoresistor | 0 | 1 | 1
Photoresistor linking to CAM | Camera | 0 | 1 | 1
Photoresistor for nightvision switch | Camera | 0 | 1 | 1
Photoresistor for nightvision switch | Photoresistor | 0 | 1 | 1
Photoresistor for nightvision switch | Raspberry Pi | 0 | 1 | 1
Creating Frame and Components | Frame materials | 0 | 1 | 1
Creating Frame and Components | 3D printer | 0 | 1 | 1
Creating Frame and Components | Prototype Frame | 0 | 1 | 1
Creating Frame and Components | Wheels | 0 | 1 | 1
3D Print Frame | 3D printer | 0 | 1 | 1
3D Print Frame | Frame materials | 0 | 1 | 1
Attach Motors to Frame | DC Motors | 0 | 1 | 1
Attach Motors to Frame | Frame materials | 0 | 1 | 1
Attach Motors to Frame | Prototype Frame | 0 | 1 | 1